## Task details Summary
Fusion | BI and OTBI
Mentors | Arun Gopalarathnam
Mohamedasifkhana Ahamedkabir
Name | Prithiviraj Sundar (2596)
Task No | Task Title | Task Description | Task Type | Planned Start Date | Planned End Date | Resource Name | Planned Hours
1 | Bi - Purchase Order Detailed Report | Bi - Purchase Order Detailed Report | Technical Support | 2021-07-28 | 2021-07-29 | roopa.ramachandran@chainsys.com, prithiviraj.sundar@chainsys.com, petchimuthu.maharajan@chainsys.com | 16
2 | Bi - AP Aging report | Bi - AP Aging report | Technical Support | 2021-07-30 | 2021-08-02 | roopa.ramachandran@chainsys.com, prithiviraj.sundar@chainsys.com, petchimuthu.maharajan@chainsys.com | 16
3 | Bi - Ar Aging report | Bi - Ar Aging report | Technical Support | 2021-08-03 | 2021-08-04 | roopa.ramachandran@chainsys.com, prithiviraj.sundar@chainsys.com, petchimuthu.maharajan@chainsys.com | 16
4 | Bi - Sales Order Detailed Report | Bi - Sales Order Detailed Report | Technical Support | 2021-08-05 | 2021-08-06 | roopa.ramachandran@chainsys.com, prithiviraj.sundar@chainsys.com, petchimuthu.maharajan@chainsys.com | 16
5 | SQL - Joins, Set Operators and Functions | SQL - Joins, Set Operators and Functions | Technical Support | 2021-08-09 | 2021-08-09 | roopa.ramachandran@chainsys.com, prithiviraj.sundar@chainsys.com, petchimuthu.maharajan@chainsys.com | 8
6 | SQL - Fusion table queries | SQL - Fusion table queries | Technical Support | 2021-08-10 | 2021-08-10 | roopa.ramachandran@chainsys.com, prithiviraj.sundar@chainsys.com, petchimuthu.maharajan@chainsys.com | 8
7 | OTBI - View Selector | OTBI - View Selector | Technical Support | 2021-08-11 | 2021-08-11 | roopa.ramachandran@chainsys.com, prithiviraj.sundar@chainsys.com, petchimuthu.maharajan@chainsys.com | 4
8 | Bi - Report Properties | Bi - Report Properties | Technical Support | 2021-08-11 | 2021-08-11 | roopa.ramachandran@chainsys.com, prithiviraj.sundar@chainsys.com, petchimuthu.maharajan@chainsys.com | 4
9 | Bi - SCM Reports | Bi - SCM Reports | Technical Support | 2021-08-12 | 2021-08-13 | roopa.ramachandran@chainsys.com, prithiviraj.sundar@chainsys.com, petchimuthu.maharajan@chainsys.com | 16